## 1. Product Overview
Item | Description
Product Name | MediClaim AI System – Medical Insurance Claim Processing Platform
Product Vision/ Purpose | To simplify medical insurance claim processing for clinics and patients by automating document handling, reducing manual errors, and enabling easy tracking of claim status.
Business Goals / Key Success factors | 1.Automate document processing using AI (OCR) to reduce manual data entry. 2.Minimize errors in claim submission and improve accuracy. 3.Reduce claim processing time for clinics and patients. 4.Provide simple and user-friendly system for non-technical users. 5.Provide simple and user-friendly system for non-technical users.
Primary Stakeholders | Clinic staff and hospital administrators Patients and caregivers Insurance agents and advisors Development Team – Backend & AI Processing Frontend Team – UI/UX Interface QA/Test Team – Testing & Validation 💯 Why this is PERFECT ✔ Matches your friend’s format ✔ Professional language (not too complex) ✔ Based 100% on your project ✔ Covers AI + real-world impact (important for marks) 🔥 Pro Tip for Viva If sir asks: 👉 “Why is this project useful?” Say: “It reduces manual effort, improves accuracy, and makes claim tracking easy for clinics and patients.” If you want next level 👇 👉 I can also help you fill: Features section (if next sheet exists) Architecture diagram Viva questions & answers Just tell me 👍 **Product Vision / Purpose** ---------------------------- To simplify medical insurance claim processing for clinics and patients by automating document handling, reducing manual errors, and enabling easy tracking of claim status. in this cell im unable to fill this full. unable to come down Ahh got it 👍 — this is just an Excel issue, not your content. You’re typing but it’s not going to the next line inside the same cell. ✅ Solution (VERY SIMPLE) 👉 Press this: ALT + ENTER 🔹 What it does: Moves text to next line inside the SAME cell Lets you write full paragraph neatly 💡 Example (how you should write): Type like this: To simplify medical insurance claim processing for clinics and patients by (ALT + ENTER) automating document handling, reducing manual errors, and (ALT + ENTER) enabling easy tracking of claim status. 🛠️ If text still not showing properly Do this: 1. Enable Wrap Text Select the cell Click Home → Wrap Text 2. Adjust Row Height Drag the row down manually OR Double click row border (auto adjust) 🚀 Pro Tip (to make it look like your friend’s sheet) Break it into 2–3 lines using ALT + ENTER 👉 Makes it look clean + professional If you want, I can: 👉 Format ALL your content exactly like your friend’s Excel (line by line)

## 2. Product Backlog
Epic ID | Epic Title | User Story ID | User Story/Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
| Major features | Mandatory | Mandatory |  |  | (optional) | Mandatory | Mandatory | Mandatory | Mandatory
E1 | User Authentication | US1 | As a user, I want to sign up using email and OTP so that I can securely access my account. | Registration screen | Must Have | 8 | In Progress | BackendDEv(Nandan P) | Verify OTP login works correctly | Yashwant TS
Email input
OTP generation
OTP verification
Login screen
Error handling
E2 | Document Upload | US2 | As a user, I want to upload claim documents so that the system can process them. | 1.File upload (PDF/Image) 2.File size validation 3.Storage system 4.Upload success/failure message | Must Have | 13 | In Progress | Frontend Dev(Nandan P) | Upload valid and invalid files | Pruthviraj k
E3 | Data Extraction | US3 | As a user, I want the system to extract details from documents automatically so that I don’t need manual entry. | 1.OCR processing 2.Extract name, date, amount 3.Data parsing 4.Error handling for unclear documents | Must Have | 20 | Completed | AI/Backend Dev (Nandan p/ Pruthviraj) | Verify extracted data accuracy | Yashwant TS
E4 | Data Review | US4 | As a user, I want to review and edit extracted data so that I can correct any mistakes. | 1.Editable form UI 2.Display extracted data 3.Save updated data 4.Validation checks | Must Have | 8 | In Progress | Frontend Dev(Nandan) | Edit and save data correctly | Yashwant TS
E5 | Claim Submission | US5 | As a user, I want to submit my claim so that it can be processed. | 1.Submit button 2.Data validation 3.Store claim in database 4.Generate claim ID | Must Have | 8 | In Progress | Backend Dev (Nandan/Pruthviraj) | Claim submission works correctly | Yashwant TS
E6 | Claim Tracking | US6 | As a user, I want to track my claim status so that I know the progress. | 1.Status display 2.Claim ID tracking 3.Status update system 4.Dashboard view | Should Have | 13 | In Progress | Frontend Dev (Nandan P) | Status updates correctly | Yashwant TS
Notes: | MoSCoW
|  | Must Have | Critical requirements that are essential for the project's success and must be delivered.
|  | Should Have | Important requirements that are highly desirable but not vital; the project can still be delivered without them, but it would be less ideal.
|  | Could Have | "Nice-to-have" requirements that are less important and have a lower impact if they are not included.
|  | Won't Have | Requirements that are not being delivered in the current project or timeframe, but may be considered for future iterations.
Story Points
|  | Fibonacci | 0,1,1,2,3,5,8,13,21,34,….
|  | (Modified) | 0,1,1,2,3,5,8,13,20 (points decided based on a User Story's complexity, effort needed & riks)
Ends at 20. Rarely extended to 40 and 100 for very large tasks.

## 3. Roadmap
Release |  | Key Features | Dependencies | Demo Status
Llist Epic Names
v0.1 | 2026-03-15 | User Authentication (E1): Signup/login with email & OTP, secure access | None | On Track
v0.2 | 2026-03-20 | Document Upload (E2): Upload claim documents (PDF/Image), file validation, storage | Storage system ready | In Progress
v0.3 | 2026-03-22 | Data Extraction (E3): OCR-based extraction of name, date, amount from documents | OCR/AI model integration | In Progress
v0.4 | 2026-03-24 | Data Review (E4): Display extracted data, allow user to edit and validate | Backend data processing | In Progress
v0.5 | 2026-03-15 | Claim Submission (E5): Submit validated claims, generate claim ID, store in database | Database integration | Planned
v1.0 | 2026-03-27 | Claim Tracking (E6): Track claim status, view updates, dashboard display | Backend + frontend integration | In Progress
v1.1 |  | System Optimization: Performance improvement, UI enhancements, bug fixes | Testing & feedback | Yet to Plan

## 4. Retrospective
Note: This is for the team to learn and improve. I have taught you in the class on Nov 4, 2025.
Ideally, the team should do this at the end of every release. How often you do , I leave it to you.
What Went Well | What Didn’t Go Well | Improvements / Action Items | Owner
Net time what will you do differently
Agile meetings (standups, planning) were conducted regularly and smoothly | Document upload and processing had delays during initial testing | Improve document handling and optimize processing speed in next sprint | Backend Lead (Nandan /Yasshwant TS)
User authentication module worked correctly and securely | Some issues in OTP verification during early stages | Enhance OTP validation and error handling | Backend Dev (Nandan P)
Data extraction (OCR) feature successfully implemented | Accuracy issues for unclear or low-quality documents | Improve OCR accuracy and handle edge cases | AI/Backend Dev (Nandan P / Pruthviraj K)
Good coordination between frontend and backend teams | Integration between modules took extra time | Improve API design and integration planning | DevOps (Pruthviraj K)
Core features like claim submission and tracking were completed | Some UI issues and minor bugs remained | Enhance UI and fix bugs before final release | Frontend Dev (Nandan P)